## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2185-swen-261-06-a Applications Anonymous
Testing Team Name | 2185-swen-261-06-a Applications Anonymous

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MA; 3/6/19 | Pass | MA; 4/8/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MA; 3/6/19 | Fail | MA; 4/8/19; board is oriented incorrectly for both users (should be a simple fix)
As a Player I want to make a simple move so that I can move one adjacent square diagonally forward. | Given that I have a piece on the board that can make a valid move, when I drag it to a valid space then the piece is moved to its location. |  |  | Pass | MA; 4/8/19
| Given that I have a piece, when I try to drag a piece onto a white space then I expect to not be able to. |  |  | Pass | MA; 4/8/19
| Given that I have a piece on the board, when I try to drag it onto a preoccupied space then I expect to not be able to. |  |  | Pass | MA; 4/8/19
| Given that it is not my turn, when I try to make a move then I expect to not be able to. |  |  | Pass | MA; 4/8/19
As a Player, I want to jump over a piece so that remove it from the board. | Given that there is an opponent piece in front of mine, when I click and drag a piece to the next diagonal space over it then the opponent's piece is removed from the board. |  |  | Fail | MA; 4/8/19; not fully implemented yet
| Given that there is one of my own pieces in front of the one I am trying to move, when I try to jump over the piece then I expect to not be able to. |  |  | Fail | MA; 4/8/19; not fully implemented yet
| Given that the piece I am trying to jump is next to a wall, when I try to jump over the piece then I expect to not be able to. |  |  | Fail | MA; 4/8/19; not fully implemented yet
As a Player I want to jump over multiple pieces so that I can remove more than one of the opponent's pieces at once. | Given that there are multiple valid jumps in a row, when I try to jump over an opponent's piece then I expect to jump over all of the pieces that I am able to. |  |  | Fail | MA; 4/8/19; not fully implemented yet
As a Player I want to reach the row of the board furthest from me with my piece so that I can make my piece a king. | Given that my piece is on the board, when I move it to the last (furthest) row then it is made into a King piece. |  |  | Fail | MA; 4/8/19; not fully implemented yet
As a Player I want to make my piece a king so that I can move my king both diagonally forward and diagonally backward. | Given that my piece is a king, when I try to move the piece then I expect to be able to move in the reverse (towards me) direction. |  |  | Fail | MA; 4/8/19; not fully implemented yet
| Given that my piece is a king, when there are opponent pieces behind me then I expect to be able to jump over them (as long as other conditions are valid). |  |  | Fail | MA; 4/8/19; not fully implemented yet
As a Player I want to be able to resign so that I can end the game at any point at the cost of losing the game. | Given that I want to leave the game, when I click the resign button then I expect to be notified that I have forfeited (and lost) the match.
Given that I am still logged into the game, when my opponent clicks the resignation button then I expect to be notified that my opponent has resigned and that I have won the match.
Given that I am still logged into the game, when my opponent disconnects from the game then I expect to be notified that my opponent has disconnected and that I have won the game.
Given that I am being told that I have won/lost the match, when I click a confirmation button then I expect to be brought back to the home screen.
As a Player I want to make my opponent run out of possible moves so that I can win the game. | Given that I am still playing the game, when I have no more possible moves to make then I am told that I have no more possible moves to make and that I have lost the game.
Given that I am still playing the game, when my opponent has no more possible moves to make then I expect to be told that my opponent has no more possible moves to make and that I have won the game.
As a Player I want to capture all of my opponent’s pieces so that I can win the game. | Given that I am playing the game, when my opponent captures my last piece then I expect to be notified that I have no more pieces left and that I have lost the game.
Given that I am playing the game, when I capture my opponent's last piece then I expect to be notified that my opponent has no more pieces on the board and that I have won the game.
As a Player I want to play a game with an available hint system so that I can request for help during my turn if I need it. | Given that I am in a game when I look at my view of the game then I should see a button to request a hint.
Given that it is my turn and that there are available moves to make, when I click the button to request a hint then I should see one valid move displayed to me.
Given that there are no valid moves for me to make, when I click the button to request a hint then I should receive a message telling me that I have no valid moves to make. (see [Win via Lack of Moves])
Given that it is not my turn, when I try to click the Hint button then I should not be able to (it should not do anything).
As a Player I want to play a game against an artificial intelligence player so that I can play checkers without a real opponent. | Given that I am logged into the home screen, when I look at the list of available players to choose from then I should see an AI player that I can start a game with.
Given that I am viewing the list of available players, when I look at the available players then I am able to differentiate between the AI computer and actual people that I can start a game with.
Given that I am in a game with a AI player, when I make a move in the game then the AI opponent will make a move on the board in response (continuing the game).